## Stock Audit Master
Borrower Name | Bank Name | Allotment Letter Date | Acceptance Letter Date | Data Requirement Sent Date (Bank) | Data Requirement Sent Date (Borrower) | Pending Details / Documents | Team Person Name | Team Person Number | Target Visit Date | Actual Visit Date | Audit Status | Review with GC / Partner Date | Report Target Date | Report Submission Date | Remarks / Delay Reason
Acme Steels Pvt Ltd | State Bank of India | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-03 | Stock statements for July 2026 pending | Priya Verma | +91 98111 22334 | 2026-08-10 | 2026-08-10 | Stock Verification Completed | 2026-08-14 | 2026-08-18 |  | Partner review scheduled for Friday
Bharat Textiles Ltd | Punjab National Bank | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-07 | Audited balance sheet FY 25-26 awaited | Amit Gupta | +91 98222 33445 | 2026-08-12 |  | Data Awaited from Borrower |  | 2026-08-20 |  | Borrower requested 3 days extension
Delta Pharmaceuticals | HDFC Bank | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-22 | None | Sneha Patel | +91 98333 44556 | 2026-07-28 | 2026-07-28 | Report Submitted | 2026-08-04 | 2026-08-08 | 2026-08-06 | Submitted to Circle Office on time