## Staff
staff_id | staff_name | role | email | daily_capacity_hrs
S01 | Rohan Mehta | Senior Associate | rohan@demo-firm.in | 8
S02 | Priya Nair | Article Assistant | priya@demo-firm.in | 8
S03 | Aman Gupta | Article Assistant | aman@demo-firm.in | 8
S04 | Sneha Iyer | Semi-Qualified | sneha@demo-firm.in | 8
S05 | Karan Desai | Article Assistant | karan@demo-firm.in | 8
S06 | Fatima Shaikh | Audit Manager | fatima@demo-firm.in | 8

## Tasks
task_id | client_name | work_type | description | assignee_id | reviewer_id | due_date | budget_hrs | status | completed_on
T101 | Shree Ganesh Traders | GST Return | GSTR-3B Aug-26 | S02 | S01 | 2026-09-20 | 6 | In Progress
T102 | Mehta Textiles Pvt Ltd | GST Return | GSTR-3B Aug-26 | S02 | S01 | 2026-09-20 | 5 | Completed | 2026-09-19
T103 | Arora Pharma Distributors | GST Return | GSTR-1 Aug-26 | S03 | S01 | 2026-09-11 | 4 | Completed | 2026-09-15
T104 | Patel Agro Exports | GST Return | GSTR-3B Aug-26 | S03 | S01 | 2026-09-20 | 5 | Completed | 2026-09-18
T105 | Greenleaf Foods Pvt Ltd | GST Return | GSTR-3B Aug-26 | S05 | S01 | 2026-09-20 | 5 | Completed | 2026-09-19
T106 | Om Sai Hardware | GST Return | GSTR-3B Aug-26 | S05 | S01 | 2026-09-20 | 3 | In Progress
T107 | Vardhan Motors | GST Return | GSTR-9 FY 2025-26 annual return | S03 | S01 | 2026-12-31 | 12 | In Progress
T201 | Mehta Textiles Pvt Ltd | Tax Audit | Form 3CA-3CD AY 2026-27 | S01 | S06 | 2026-09-30 | 40 | In Progress
T202 | Arora Pharma Distributors | Tax Audit | Form 3CB-3CD AY 2026-27 | S04 | S06 | 2026-09-30 | 35 | In Progress
T203 | Vardhan Motors | Tax Audit | Form 3CB-3CD AY 2026-27 | S04 | S06 | 2026-09-30 | 30 | In Progress
T204 | Kapoor & Sons | Tax Audit | Form 3CB-3CD AY 2026-27 | S01 | S06 | 2026-09-30 | 25 | In Progress
T205 | Patel Agro Exports | Tax Audit | Form 3CB-3CD AY 2026-27 | S04 | S06 | 2026-09-30 | 30 | In Progress
T301 | Greenleaf Foods Pvt Ltd | Statutory Audit | Statutory audit FY 2025-26 | S06 | S06 | 2026-09-28 | 60 | In Progress
T302 | Bluewave Tech Solutions Pvt Ltd | Statutory Audit | Statutory audit FY 2025-26 | S01 | S06 | 2026-10-15 | 50 | In Progress
T303 | Mehta Textiles Pvt Ltd | Statutory Audit | Statutory audit FY 2025-26 | S04 | S06 | 2026-09-26 | 45 | In Progress
T401 | Sunrise Hospitality LLP | ITR Filing | ITR-5 AY 2026-27 (audit case) | S05 | S01 | 2026-10-31 | 8 | In Progress
T402 | Kapoor & Sons | ITR Filing | ITR-5 AY 2026-27 (audit case) | S05 | S01 | 2026-10-31 | 6 | Not Started
T403 | Shree Ganesh Traders | ITR Filing | ITR-3 proprietor AY 2026-27 | S02 | S01 | 2026-10-31 | 6 | In Progress
T404 | Om Sai Hardware | ITR Filing | ITR-3 proprietor AY 2026-27 (belated review) | S02 | S01 | 2026-09-15 | 6 | Completed | 2026-09-14
T501 | Bluewave Tech Solutions Pvt Ltd | TDS Return | 24Q/26Q Q2 FY 2026-27 | S03 | S01 | 2026-10-31 | 6 | Not Started
T502 | Greenleaf Foods Pvt Ltd | TDS Return | 26Q Q1 FY 2026-27 correction | S03 | S01 | 2026-09-30 | 5 | In Progress
T601 | Bluewave Tech Solutions Pvt Ltd | ROC Compliance | AOC-4 and MGT-7 FY 2025-26 | S04 | S06 | 2026-10-29 | 8 | In Progress
T602 | Greenleaf Foods Pvt Ltd | ROC Compliance | DIR-3 KYC for directors | S05 | S01 | 2026-09-30 | 2 | Completed | 2026-09-16

## Timesheet
entry_id | date | staff_id | task_id | client_name | hours | narration
TS0001 | 2026-09-09 | S01 | T201 | Mehta Textiles Pvt Ltd | 3 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Mehta Textiles Pvt Ltd
TS0002 | 2026-09-09 | S01 | T201 | Mehta Textiles Pvt Ltd | 3 | Verified TDS compliance for clause 34 of Form 3CD - Mehta Textiles Pvt Ltd
TS0003 | 2026-09-09 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 2 | Drafted audit observations for management letter - Bluewave Tech Solutions Pvt Ltd
TS0004 | 2026-09-09 | S02 | T403 | Shree Ganesh Traders | 2.5 | discussion
TS0005 | 2026-09-09 | S03 | T103 | Arora Pharma Distributors | 1 | Followed up with client for pending sales invoices for GST return - Arora Pharma Distributors
TS0006 | 2026-09-09 | S04 | T202 | Arora Pharma Distributors | 1.5 | Verified TDS compliance for clause 34 of Form 3CD - Arora Pharma Distributors
TS0007 | 2026-09-09 | S04 | T205 | Patel Agro Exports | 1.5 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Patel Agro Exports
TS0008 | 2026-09-09 | S04 | T303 | Mehta Textiles Pvt Ltd | 2 | Verified bank reconciliation statements for statutory audit - Mehta Textiles Pvt Ltd
TS0009 | 2026-09-09 | S04 | T303 | Mehta Textiles Pvt Ltd | 1 | Reviewed fixed asset register and physical verification report - Mehta Textiles Pvt Ltd
TS0010 | 2026-09-09 | S05 | T602 | Greenleaf Foods Pvt Ltd | 1.5 | Prepared AOC-4 draft with financial statements - Greenleaf Foods Pvt Ltd
TS0011 | 2026-09-09 | S06 | T301 | Greenleaf Foods Pvt Ltd | 2.5 | Obtained and tested debtor balance confirmations for audit - Greenleaf Foods Pvt Ltd
TS0012 | 2026-09-09 | S06 | T301 | Greenleaf Foods Pvt Ltd | 6 | Vouching of purchase ledger for statutory audit - Greenleaf Foods Pvt Ltd
TS0013 | 2026-09-10 | S01 | T201 | Mehta Textiles Pvt Ltd | 2.5 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Mehta Textiles Pvt Ltd
TS0014 | 2026-09-10 | S01 | T204 | Kapoor & Sons | 2 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Kapoor & Sons
TS0015 | 2026-09-10 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 1.5 | Drafted audit observations for management letter - Bluewave Tech Solutions Pvt Ltd
TS0016 | 2026-09-10 | S01 | T204 | Kapoor & Sons | 2.5 | Prepared GSTR-3B working and tax liability computation - Kapoor & Sons
TS0017 | 2026-09-10 | S02 | T404 | Om Sai Hardware | 2 | Prepared computation of income for AY 2026-27 - Om Sai Hardware
TS0018 | 2026-09-10 | S03 | T999 | Unknown Client | 2.5 | Prepared GSTR-3B working for new client
TS0019 | 2026-09-10 | S04 | T205 | Patel Agro Exports | 3 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Patel Agro Exports
TS0020 | 2026-09-10 | S04 | T303 | Mehta Textiles Pvt Ltd | 2.5 | Drafted audit observations for management letter - Mehta Textiles Pvt Ltd
TS0021 | 2026-09-10 | S04 | T303 | Mehta Textiles Pvt Ltd | 1.5 | Verified revenue cut-off and sales vouching for audit - Mehta Textiles Pvt Ltd
TS0022 | 2026-09-10 | S05 | T401 | Sunrise Hospitality LLP | 1.5 | Reconciled AIS / 26AS with books before ITR filing - Sunrise Hospitality LLP
TS0023 | 2026-09-10 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1.5 | Obtained and tested debtor balance confirmations for audit - Greenleaf Foods Pvt Ltd
TS0024 | 2026-09-10 | S06 | T301 | Greenleaf Foods Pvt Ltd | 3 | Verified revenue cut-off and sales vouching for audit - Greenleaf Foods Pvt Ltd
TS0025 | 2026-09-10 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1.5 | Drafted audit observations for management letter - Greenleaf Foods Pvt Ltd
TS0026 | 2026-09-11 | S01 | T201 | Mehta Textiles Pvt Ltd | 2.5 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Mehta Textiles Pvt Ltd
TS0027 | 2026-09-11 | S01 | T204 | Kapoor & Sons | 2.5 | Checked cash payments above Rs 10,000 for 40A(3) disallowance (tax audit) - Kapoor & Sons
TS0028 | 2026-09-11 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 1.5 | Reviewed fixed asset register and physical verification report - Bluewave Tech Solutions Pvt Ltd
TS0029 | 2026-09-11 | S02 | T102 | Mehta Textiles Pvt Ltd | 3 | Followed up with client for pending sales invoices for GST return - Mehta Textiles Pvt Ltd
TS0030 | 2026-09-11 | S03 | T104 | Patel Agro Exports | 3 | Followed up with client for pending sales invoices for GST return - Patel Agro Exports
TS0031 | 2026-09-11 | S04 | T205 | Patel Agro Exports | 1 | Verified clause 44 expenditure break-up for Form 3CD - Patel Agro Exports
TS0032 | 2026-09-11 | S04 | T303 | Mehta Textiles Pvt Ltd | 1.5 | Verified revenue cut-off and sales vouching for audit - Mehta Textiles Pvt Ltd
TS0033 | 2026-09-11 | S04 | T303 | Mehta Textiles Pvt Ltd | 1.5 | Drafted audit observations for management letter - Mehta Textiles Pvt Ltd
TS0034 | 2026-09-11 | S04 | T303 | Mehta Textiles Pvt Ltd | 1.5 | Verified bank reconciliation statements for statutory audit - Mehta Textiles Pvt Ltd
TS0035 | 2026-09-11 | S04 | T303 | Mehta Textiles Pvt Ltd | 3 | Verified revenue cut-off and sales vouching for audit - Mehta Textiles Pvt Ltd
TS0036 | 2026-09-11 | S05 | T106 | Om Sai Hardware | 2.5 | Followed up with client for pending sales invoices for GST return - Om Sai Hardware
TS0037 | 2026-09-11 | S06 | T301 | Greenleaf Foods Pvt Ltd | 3 | Vouching of purchase ledger for statutory audit - Greenleaf Foods Pvt Ltd
TS0038 | 2026-09-11 | S06 | T301 | Greenleaf Foods Pvt Ltd | 3 | Verified revenue cut-off and sales vouching for audit - Greenleaf Foods Pvt Ltd
TS0039 | 2026-09-11 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1 | Drafted audit observations for management letter - Greenleaf Foods Pvt Ltd
TS0040 | 2026-09-12 | S01 | T201 | Mehta Textiles Pvt Ltd | 1.5 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Mehta Textiles Pvt Ltd
TS0041 | 2026-09-12 | S01 | T201 | Mehta Textiles Pvt Ltd | 2 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Mehta Textiles Pvt Ltd
TS0042 | 2026-09-12 | S01 | T204 | Kapoor & Sons | 2 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Kapoor & Sons
TS0043 | 2026-09-12 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 2 | Verified bank reconciliation statements for statutory audit - Bluewave Tech Solutions Pvt Ltd
TS0044 | 2026-09-12 | S02 | T404 | Om Sai Hardware | 1.5 | Reconciled AIS / 26AS with books before ITR filing - Om Sai Hardware
TS0045 | 2026-09-12 | S03 | T103 | Arora Pharma Distributors | 1.5 | Reviewed e-invoice / e-way bill data against sales register for GST - Arora Pharma Distributors
TS0046 | 2026-09-12 | S04 | T202 | Arora Pharma Distributors | 3 | Verified clause 44 expenditure break-up for Form 3CD - Arora Pharma Distributors
TS0047 | 2026-09-12 | S04 | T205 | Patel Agro Exports | 1 | Verified clause 44 expenditure break-up for Form 3CD - Patel Agro Exports
TS0048 | 2026-09-12 | S04 | T303 | Mehta Textiles Pvt Ltd | 1 | Vouching of purchase ledger for statutory audit - Mehta Textiles Pvt Ltd
TS0049 | 2026-09-12 | S04 | T303 | Mehta Textiles Pvt Ltd | 3 | Obtained and tested debtor balance confirmations for audit - Mehta Textiles Pvt Ltd
TS0050 | 2026-09-12 | S05 | T204 | Kapoor & Sons | 3 | Checked 40A(3) cash payments for tax audit - Kapoor & Sons
TS0051 | 2026-09-12 | S06 | T301 | Greenleaf Foods Pvt Ltd | 3 | Obtained and tested debtor balance confirmations for audit - Greenleaf Foods Pvt Ltd
TS0052 | 2026-09-12 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1 | Verified bank reconciliation statements for statutory audit - Greenleaf Foods Pvt Ltd
TS0053 | 2026-09-12 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1 | Drafted audit observations for management letter - Greenleaf Foods Pvt Ltd
TS0054 | 2026-09-12 | S06 | T301 | Greenleaf Foods Pvt Ltd | 2.5 | Verified revenue cut-off and sales vouching for audit - Greenleaf Foods Pvt Ltd
TS0055 | 2026-09-14 | S01 | T201 | Mehta Textiles Pvt Ltd | 2.5 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Mehta Textiles Pvt Ltd
TS0056 | 2026-09-14 | S01 | T204 | Kapoor & Sons | 3 | Checked cash payments above Rs 10,000 for 40A(3) disallowance (tax audit) - Kapoor & Sons
TS0057 | 2026-09-14 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 2.5 | Drafted audit observations for management letter - Bluewave Tech Solutions Pvt Ltd
TS0058 | 2026-09-14 | S02 | T101 | Shree Ganesh Traders | 3 | Vouching of purchase ledger for statutory audit - Shree Ganesh Traders
TS0059 | 2026-09-14 | S03 | T107 | Vardhan Motors | 1.5 | Reviewed e-invoice / e-way bill data against sales register for GST - Vardhan Motors
TS0060 | 2026-09-14 | S04 | T205 | Patel Agro Exports | 2 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Patel Agro Exports
TS0061 | 2026-09-14 | S04 | T303 | Mehta Textiles Pvt Ltd | 1 | Vouching of purchase ledger for statutory audit - Mehta Textiles Pvt Ltd
TS0062 | 2026-09-14 | S04 | T303 | Mehta Textiles Pvt Ltd | 2 | Reviewed fixed asset register and physical verification report - Mehta Textiles Pvt Ltd
TS0063 | 2026-09-14 | S04 | T601 | Bluewave Tech Solutions Pvt Ltd | 2 | Collected director KYC documents for DIR-3 KYC - Bluewave Tech Solutions Pvt Ltd
TS0064 | 2026-09-14 | S05 | T105 | Greenleaf Foods Pvt Ltd | 1 | Checked RCM liability and blocked credits u/s 17(5) for GST return - Greenleaf Foods Pvt Ltd
TS0065 | 2026-09-14 | S06 | T301 | Greenleaf Foods Pvt Ltd | 4 | Reviewed fixed asset register and physical verification report - Greenleaf Foods Pvt Ltd
TS0066 | 2026-09-14 | S06 | T301 | Greenleaf Foods Pvt Ltd | 3 | Verified bank reconciliation statements for statutory audit - Greenleaf Foods Pvt Ltd
TS0067 | 2026-09-15 | S01 | T201 | Mehta Textiles Pvt Ltd | 1.5 | Checked cash payments above Rs 10,000 for 40A(3) disallowance (tax audit) - Mehta Textiles Pvt Ltd
TS0068 | 2026-09-15 | S01 | T204 | Kapoor & Sons | 1.5 | Verified TDS compliance for clause 34 of Form 3CD - Kapoor & Sons
TS0069 | 2026-09-15 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 2.5 | Drafted audit observations for management letter - Bluewave Tech Solutions Pvt Ltd
TS0070 | 2026-09-15 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 0.5 | Verified bank reconciliation statements for statutory audit - Bluewave Tech Solutions Pvt Ltd
TS0071 | 2026-09-15 | S02 | T101 | Shree Ganesh Traders | 0.5 | Prepared GSTR-3B working and tax liability computation - Shree Ganesh Traders
TS0072 | 2026-09-15 | S03 | T103 | Arora Pharma Distributors | 1 | Checked RCM liability and blocked credits u/s 17(5) for GST return - Arora Pharma Distributors
TS0073 | 2026-09-15 | S04 | T205 | Patel Agro Exports | 1.5 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Patel Agro Exports
TS0074 | 2026-09-15 | S04 | T303 | Mehta Textiles Pvt Ltd | 2 | Drafted audit observations for management letter - Mehta Textiles Pvt Ltd
TS0075 | 2026-09-15 | S04 | T303 | Mehta Textiles Pvt Ltd | 1 | Reviewed fixed asset register and physical verification report - Mehta Textiles Pvt Ltd
TS0076 | 2026-09-15 | S04 | T303 | Mehta Textiles Pvt Ltd | 1.5 | Verified bank reconciliation statements for statutory audit - Mehta Textiles Pvt Ltd
TS0077 | 2026-09-15 | S05 | T401 | Sunrise Hospitality LLP | 3 | office work
TS0078 | 2026-09-15 | S06 | T301 | Greenleaf Foods Pvt Ltd | 2 | Verified revenue cut-off and sales vouching for audit - Greenleaf Foods Pvt Ltd
TS0079 | 2026-09-15 | S06 | T301 | Greenleaf Foods Pvt Ltd | 2.5 | Verified bank reconciliation statements for statutory audit - Greenleaf Foods Pvt Ltd
TS0080 | 2026-09-16 | S01 | T201 | Mehta Textiles Pvt Ltd | 2 | Checked cash payments above Rs 10,000 for 40A(3) disallowance (tax audit) - Mehta Textiles Pvt Ltd
TS0081 | 2026-09-16 | S01 | T201 | Mehta Textiles Pvt Ltd | 2 | Verified clause 44 expenditure break-up for Form 3CD - Mehta Textiles Pvt Ltd
TS0082 | 2026-09-16 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 3 | Vouching of purchase ledger for statutory audit - Bluewave Tech Solutions Pvt Ltd
TS0083 | 2026-09-16 | S02 | T102 | Mehta Textiles Pvt Ltd | 0.5 | Followed up with client for pending sales invoices for GST return - Mehta Textiles Pvt Ltd
TS0084 | 2026-09-16 | S03 | T104 | Patel Agro Exports | 1 | Followed up with client for pending sales invoices for GST return - Patel Agro Exports
TS0085 | 2026-09-16 | S04 | T205 | Patel Agro Exports | 1 | Checked cash payments above Rs 10,000 for 40A(3) disallowance (tax audit) - Patel Agro Exports
TS0086 | 2026-09-16 | S04 | T205 | Patel Agro Exports | 0.5 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Patel Agro Exports
TS0087 | 2026-09-16 | S04 | T303 | Mehta Textiles Pvt Ltd | 1 | Vouching of purchase ledger for statutory audit - Mehta Textiles Pvt Ltd
TS0088 | 2026-09-16 | S04 | T303 | Mehta Textiles Pvt Ltd | 1.5 | Obtained and tested debtor balance confirmations for audit - Mehta Textiles Pvt Ltd
TS0089 | 2026-09-16 | S04 | T303 | Mehta Textiles Pvt Ltd | 1.5 | Verified revenue cut-off and sales vouching for audit - Mehta Textiles Pvt Ltd
TS0090 | 2026-09-16 | S05 | T105 | Greenleaf Foods Pvt Ltd | 1.5 | Prepared GSTR-3B working and tax liability computation - Greenleaf Foods Pvt Ltd
TS0091 | 2026-09-16 | S06 | T301 | Greenleaf Foods Pvt Ltd | 3 | Vouching of purchase ledger for statutory audit - Greenleaf Foods Pvt Ltd
TS0092 | 2026-09-16 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1.5 | Reviewed fixed asset register and physical verification report - Greenleaf Foods Pvt Ltd
TS0093 | 2026-09-16 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1.5 | Obtained and tested debtor balance confirmations for audit - Greenleaf Foods Pvt Ltd
TS0094 | 2026-09-17 | S01 | T201 | Mehta Textiles Pvt Ltd | 2 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Mehta Textiles Pvt Ltd
TS0095 | 2026-09-17 | S01 | T204 | Kapoor & Sons | 3 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Kapoor & Sons
TS0096 | 2026-09-17 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 2 | Verified bank reconciliation statements for statutory audit - Bluewave Tech Solutions Pvt Ltd
TS0097 | 2026-09-17 | S02 | T101 | Shree Ganesh Traders | 1 | Downloaded GSTR-2B and reconciled ITC with purchase register - Shree Ganesh Traders
TS0098 | 2026-09-17 | S03 | T107 | Vardhan Motors | 4 | misc work
TS0099 | 2026-09-17 | S04 | T205 | Patel Agro Exports | 3 | Checked cash payments above Rs 10,000 for 40A(3) disallowance (tax audit) - Patel Agro Exports
TS0100 | 2026-09-17 | S04 | T303 | Mehta Textiles Pvt Ltd | 2 | Verified bank reconciliation statements for statutory audit - Mehta Textiles Pvt Ltd
TS0101 | 2026-09-17 | S04 | T303 | Mehta Textiles Pvt Ltd | 1.5 | Verified revenue cut-off and sales vouching for audit - Mehta Textiles Pvt Ltd
TS0102 | 2026-09-17 | S05 | T401 | Sunrise Hospitality LLP | 1.5 | Prepared computation of income for AY 2026-27 - Sunrise Hospitality LLP
TS0103 | 2026-09-17 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1.5 | Obtained and tested debtor balance confirmations for audit - Greenleaf Foods Pvt Ltd
TS0104 | 2026-09-17 | S06 | T301 | Greenleaf Foods Pvt Ltd | 5 | Vouching of purchase ledger for statutory audit - Greenleaf Foods Pvt Ltd
TS0105 | 2026-09-18 | S01 | T201 | Mehta Textiles Pvt Ltd | 1 | Verified clause 44 expenditure break-up for Form 3CD - Mehta Textiles Pvt Ltd
TS0106 | 2026-09-18 | S01 | T201 | Mehta Textiles Pvt Ltd | 0.5 | Verified TDS compliance for clause 34 of Form 3CD - Mehta Textiles Pvt Ltd
TS0107 | 2026-09-18 | S01 | T204 | Kapoor & Sons | 2.5 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Kapoor & Sons
TS0108 | 2026-09-18 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 1 | Drafted audit observations for management letter - Bluewave Tech Solutions Pvt Ltd
TS0109 | 2026-09-18 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 3 | Verified bank reconciliation statements for statutory audit - Bluewave Tech Solutions Pvt Ltd
TS0110 | 2026-09-18 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 3 | Verified bank reconciliation statements for statutory audit - Bluewave Tech Solutions Pvt Ltd
TS0111 | 2026-09-18 | S03 | T502 | Greenleaf Foods Pvt Ltd | 2 | Prepared challan-wise TDS working for TDS return - Greenleaf Foods Pvt Ltd
TS0112 | 2026-09-18 | S04 | T205 | Patel Agro Exports | 2 | Verified clause 44 expenditure break-up for Form 3CD - Patel Agro Exports
TS0113 | 2026-09-18 | S04 | T303 | Mehta Textiles Pvt Ltd | 2.5 | Reviewed fixed asset register and physical verification report - Mehta Textiles Pvt Ltd
TS0114 | 2026-09-18 | S04 | T303 | Mehta Textiles Pvt Ltd | 1.5 | Vouching of purchase ledger for statutory audit - Mehta Textiles Pvt Ltd
TS0115 | 2026-09-18 | S05 | T105 | Greenleaf Foods Pvt Ltd | 2 | Checked RCM liability and blocked credits u/s 17(5) for GST return - Greenleaf Foods Pvt Ltd
TS0116 | 2026-09-18 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1 | Obtained and tested debtor balance confirmations for audit - Greenleaf Foods Pvt Ltd
TS0117 | 2026-09-18 | S06 | T301 | Greenleaf Foods Pvt Ltd | 2.5 | Verified revenue cut-off and sales vouching for audit - Greenleaf Foods Pvt Ltd
TS0118 | 2026-09-18 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1 | Verified bank reconciliation statements for statutory audit - Greenleaf Foods Pvt Ltd
TS0119 | 2026-09-19 | S01 | T201 | Mehta Textiles Pvt Ltd | 1 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Mehta Textiles Pvt Ltd
TS0120 | 2026-09-19 | S01 | T204 | Kapoor & Sons | 1.5 | Checked cash payments above Rs 10,000 for 40A(3) disallowance (tax audit) - Kapoor & Sons
TS0121 | 2026-09-19 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 1 | Vouching of purchase ledger for statutory audit - Bluewave Tech Solutions Pvt Ltd
TS0122 | 2026-09-19 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 3 | Reviewed fixed asset register and physical verification report - Bluewave Tech Solutions Pvt Ltd
TS0123 | 2026-09-19 | S02 | T102 | Mehta Textiles Pvt Ltd | 1 | Prepared GSTR-3B working and tax liability computation - Mehta Textiles Pvt Ltd
TS0124 | 2026-09-19 | S03 | T107 | Vardhan Motors | 0.5 | Checked RCM liability and blocked credits u/s 17(5) for GST return - Vardhan Motors
TS0125 | 2026-09-19 | S03 | T502 | Greenleaf Foods Pvt Ltd | 2 | Prepared computation of income and filed ITR for director - Greenleaf Foods Pvt Ltd
TS0126 | 2026-09-19 | S04 | T205 | Patel Agro Exports | 1 | Verified clause 44 expenditure break-up for Form 3CD - Patel Agro Exports
TS0127 | 2026-09-19 | S04 | T205 | Patel Agro Exports | 2.5 | Verified TDS compliance for clause 34 of Form 3CD - Patel Agro Exports
TS0128 | 2026-09-19 | S04 | T303 | Mehta Textiles Pvt Ltd | 2.5 | Drafted audit observations for management letter - Mehta Textiles Pvt Ltd
TS0129 | 2026-09-19 | S04 | T303 | Mehta Textiles Pvt Ltd | 1 | Reviewed fixed asset register and physical verification report - Mehta Textiles Pvt Ltd
TS0130 | 2026-09-19 | S06 | T301 | Greenleaf Foods Pvt Ltd | 2.5 | Verified bank reconciliation statements for statutory audit - Greenleaf Foods Pvt Ltd
TS0131 | 2026-09-19 | S06 | T301 | Greenleaf Foods Pvt Ltd | 2.5 | Reviewed fixed asset register and physical verification report - Greenleaf Foods Pvt Ltd
TS0132 | 2026-09-19 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1 | Drafted audit observations for management letter - Greenleaf Foods Pvt Ltd
TS0133 | 2026-09-21 | S01 | T201 | Mehta Textiles Pvt Ltd | 1 | Verified clause 44 expenditure break-up for Form 3CD - Mehta Textiles Pvt Ltd
TS0134 | 2026-09-21 | S01 | T204 | Kapoor & Sons | 1 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Kapoor & Sons
TS0135 | 2026-09-21 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 2.5 | Reviewed fixed asset register and physical verification report - Bluewave Tech Solutions Pvt Ltd
TS0136 | 2026-09-21 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 3 | Vouching of purchase ledger for statutory audit - Bluewave Tech Solutions Pvt Ltd
TS0137 | 2026-09-21 | S02 | T404 | Om Sai Hardware | 2 | Revised computation and uploaded ITR for Om Sai Hardware
TS0138 | 2026-09-21 | S03 | T502 | Greenleaf Foods Pvt Ltd | 1 | Prepared challan-wise TDS working for TDS return - Greenleaf Foods Pvt Ltd
TS0139 | 2026-09-21 | S04 | T202 | Arora Pharma Distributors | 1.5 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Arora Pharma Distributors
TS0140 | 2026-09-21 | S04 | T205 | Patel Agro Exports | 2.5 | Checked cash payments above Rs 10,000 for 40A(3) disallowance (tax audit) - Patel Agro Exports
TS0141 | 2026-09-21 | S04 | T303 | Mehta Textiles Pvt Ltd | 4 | Verified revenue cut-off and sales vouching for audit - Mehta Textiles Pvt Ltd
TS0142 | 2026-09-21 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1 | Verified bank reconciliation statements for statutory audit - Greenleaf Foods Pvt Ltd
TS0143 | 2026-09-21 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1.5 | Vouching of purchase ledger for statutory audit - Greenleaf Foods Pvt Ltd
TS0144 | 2026-09-21 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1 | Drafted audit observations for management letter - Greenleaf Foods Pvt Ltd
TS0145 | 2026-09-22 | S01 | T201 | Mehta Textiles Pvt Ltd | 2.5 | Verified clause 44 expenditure break-up for Form 3CD - Mehta Textiles Pvt Ltd
TS0146 | 2026-09-22 | S01 | T201 | Mehta Textiles Pvt Ltd | 1.5 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Mehta Textiles Pvt Ltd
TS0147 | 2026-09-22 | S01 | T204 | Kapoor & Sons | 1 | Drafted Form 3CD clauses 20 to 30 and discussed with manager - Kapoor & Sons
TS0148 | 2026-09-22 | S01 | T302 | Bluewave Tech Solutions Pvt Ltd | 2 | Vouching of purchase ledger for statutory audit - Bluewave Tech Solutions Pvt Ltd
TS0149 | 2026-09-22 | S02 | T403 | Shree Ganesh Traders | 2 | Reconciled AIS / 26AS with books before ITR filing - Shree Ganesh Traders
TS0150 | 2026-09-22 | S03 | T107 | Vardhan Motors | 2 | Prepared GSTR-3B working and tax liability computation - Vardhan Motors
TS0151 | 2026-09-22 | S04 | T205 | Patel Agro Exports | 1.5 | Verified depreciation as per Income-tax Act for clause 18 of 3CD - Patel Agro Exports
TS0152 | 2026-09-22 | S04 | T303 | Mehta Textiles Pvt Ltd | 2.5 | Reviewed fixed asset register and physical verification report - Mehta Textiles Pvt Ltd
TS0153 | 2026-09-22 | S04 | T303 | Mehta Textiles Pvt Ltd | 3 | Drafted audit observations for management letter - Mehta Textiles Pvt Ltd
TS0154 | 2026-09-22 | S04 | T303 | Mehta Textiles Pvt Ltd | 2.5 | Vouching of purchase ledger for statutory audit - Mehta Textiles Pvt Ltd
TS0155 | 2026-09-22 | S06 | T301 | Greenleaf Foods Pvt Ltd | 1.5 | Obtained and tested debtor balance confirmations for audit - Greenleaf Foods Pvt Ltd
TS0156 | 2026-09-22 | S06 | T301 | Greenleaf Foods Pvt Ltd | 2.5 | Vouching of purchase ledger for statutory audit - Greenleaf Foods Pvt Ltd
TS0157 | 2026-09-22 | S06 | T301 | Greenleaf Foods Pvt Ltd | 3 | Drafted audit observations for management letter - Greenleaf Foods Pvt Ltd
TS0158 | 2026-09-22 | S06 | T301 | Greenleaf Foods Pvt Ltd | 5 | Finalised audit working papers and closing entries review - Greenleaf Foods Pvt Ltd

## Evidence
evidence_id | task_id | evidence_type | reference_no | evidence_date | source
E01 | T102 | GST ARN | AA2709260012345 | 2026-09-19 | Gmail - GST portal acknowledgement
E02 | T104 | GST ARN | AA2409260098765 | 2026-09-18 | Gmail - GST portal acknowledgement
E03 | T106 | GST ARN | AA2709260055511 | 2026-09-21 | Gmail - GST portal acknowledgement
E04 | T404 | ITR-V Acknowledgement | ACK 812345678901234 | 2026-09-14 | Gmail - Income-tax portal
E05 | T602 | DIR-3 KYC SRN | AB1234567 | 2026-09-16 | Gmail - MCA portal