## Accuracy
Metric | Result
Planted issues | 20
Detected | 20
Missed | 0
False alarms (flagged but not planted) | 0
Detection rate | 100%
Rule-based issues caught | 14 of 14
AI (Gemini) narration issues caught | 6 of 6, identical in 2 independent runs
Data tested | 23 tasks, 158 timesheet entries (314 hrs), 6 staff, 5 filing acknowledgements
Run time | About 2 minutes per daily run in n8n

## Answer_Key
issue_id | rule | detector | task_id | staff_id | date | description | Detected by watchdog?
P01 | OVERDUE | Rule | T101 | S02 |  | GSTR-3B Aug-26 for Shree Ganesh Traders was due 20-Sep and is still open | Yes
P02 | DUE_SOON_LOW_PROGRESS | Rule | T202 | S04 |  | Tax audit (Arora Pharma) due 30-Sep with only ~17% of budget logged | Yes
P03 | DUE_SOON_LOW_PROGRESS | Rule | T203 | S04 |  | Tax audit (Vardhan Motors) due 30-Sep with zero hours logged | Yes
P04 | BUDGET_OVERRUN | Rule | T301 | S06 |  | Statutory audit Greenleaf Foods: 74 hrs vs 60 budgeted | Yes
P05 | BUDGET_OVERRUN | Rule | T303 | S04 |  | Statutory audit Mehta Textiles: logged hours exceed 45-hr budget | Yes
P06 | COMPLETED_NO_EVIDENCE | Rule | T103 | S03 |  | GSTR-1 Arora Pharma marked Completed but no ARN / acknowledgement on file | Yes
P07 | COMPLETED_NO_EVIDENCE | Rule | T105 | S05 |  | GSTR-3B Greenleaf Foods marked Completed but no ARN on file | Yes
P08 | EVIDENCE_BUT_OPEN | Rule | T106 | S05 |  | GSTR-3B Om Sai Hardware filed (ARN received) but task still In Progress | Yes
P09 | OVERLOAD | Rule |  | S04 |  | Sneha Iyer has far more budgeted hours due in the next 7 days than capacity | Yes
P10 | HOURS_AFTER_COMPLETION | Rule | T404 | S02 | 2026-09-21 | 2 hrs logged on ITR task after it was marked completed on 14-Sep | Yes
P11 | NOT_ASSIGNED | Rule | T204 | S05 | 2026-09-12 | Karan Desai booked 3 hrs to Kapoor & Sons tax audit, which is not assigned to him | Yes
P12 | UNKNOWN_TASK | Rule | T999 | S03 | 2026-09-10 | Timesheet refers to task T999 which does not exist in the task master | Yes
P13 | DUPLICATE_ENTRY | Rule | T302 | S01 | 2026-09-18 | Same 3-hr entry for Bluewave statutory audit booked twice on the same day | Yes
P14 | LONG_DAY | Rule |  | S06 | 2026-09-22 | Fatima Shaikh logged more than 11 hrs on 2026-09-22 | Yes
P15 | VAGUE_NARRATION | AI | T107 | S03 | 2026-09-17 | 4 hrs described only as 'misc work' | Yes
P16 | VAGUE_NARRATION | AI | T401 | S05 | 2026-09-15 | 3 hrs described only as 'office work' | Yes
P17 | VAGUE_NARRATION | AI | T403 | S02 | 2026-09-09 | 2.5 hrs described only as 'discussion' | Yes
P18 | NARRATION_MISMATCH | AI | T101 | S02 | 2026-09-14 | Statutory-audit vouching booked against a GSTR-3B task | Yes
P19 | NARRATION_MISMATCH | AI | T502 | S03 | 2026-09-19 | ITR computation booked against a TDS return correction task | Yes
P20 | NARRATION_MISMATCH | AI | T204 | S01 | 2026-09-10 | GST return work booked against a tax audit task | Yes