## Closeout Summary
Ledger Sentinel — Project Closeout Summary
AICA Level 2 Capstone Project · Prepared by Rupalakshmi · Closed out 2026-10-15, updated 2026-10-16 (vendor-ledger Rule 11 added)
Final Fraud-Detection Results (corrected, reproducible)
Metric | Value | Detail
Fraud caught unambiguously | 57.9% | 161 of 278 planted fraud entries; 165 flagged, 4 false positives
Fraud caught incl. tied/borderline band | 72.3% | 201 of 278; 328 flagged, 163 of them tied on the exact cutoff score — a batch for auditor review, not silently included
Fraud types at perfect catch rate | 6 / 9 | Backdated, round amount, same user, old voucher, vendor bank-detail (100% under both tiers), plus amount-under-limit (0% unambiguous → 100% once the borderline band is reviewed)
Total vouchers screened (full dataset) | 7,778 | Synthetic UAE trading-company dataset, 1 year — now includes a dedicated ledger per vendor (Accounts Payable - <Vendor>)
Planted fraud entries (answer key) | 278 | 9 distinct fraud patterns (added: structured disbursement to a single vendor, 13 entries — see Rule 11 below)
Rule 11 (vendor structuring screen, NEW) | 10 / 13 | 0 false positives against the 15 other vendor ledgers; the 10 single-entry rules above catch 0 of these 13 by design
Combined (10 rules + Rule 11) | 61.5% – 75.9% | 171–211 of 278; Rule 11's 10 catches are pure upside, zero overlap with the 10 single-entry rules
Methodology note: an earlier unstable sort made the catch rate non-reproducible (186/189/190 observed across runs) because vouchers tied on the exact same risk score straddled a hard top-N cutoff. Fixed with a stable sort + voucher_id tiebreak, reported as two honest tiers. This pass added a 9th fraud type (structuring) that the 10 single-entry rules cannot see by design, plus Rule 11 — a new, separate vendor-level screen — to catch it. Adding a fraud type the old rules can't see lowers their standalone catch rate (64.9%/74.0% → 57.9%/72.3%) while Rule 11 adds pure upside on top (61.5%–75.9% combined). Re-verified by running the full pipeline three times on freshly regenerated data with identical results.
Live Tally Integration (Step 10 / Step 1 of closeout)
Metric | Value | Detail
Vouchers pulled live (verification run) | 72 | Dated 1-Jan slice, 2 flagged near approval limit, 0 high-risk
Vouchers pulled live (closing re-verification) | 76 | Dated 31-Dec (year-end) slice, all 76 flagged on "near period end", 0 high-risk — honest date-clustering artifact, not a fraud spike
One-click pipeline | Live | run_live_fraud_scan.py — pulls, scores, and writes Excel in a single command
Ledger masters created in Tally | 27 / 27 | Zero errors
Synthetic vouchers created in Tally | ~624 | Repeatable result; Educational-edition daily creation cap, not a bug
Deliverables — Status at Closeout
File | What it is | Status
ledger_sentinel_rules.py | Shared rules module + scoring function | Updated — added Rule 11 (vendor structuring screen), kept separate from risk_score
rules_engine.py | Full 7,778-voucher scoring run (Step 2) | Updated — also validates Rule 11 separately, plus combined totals
run_live_fraud_scan.py | One-click live Tally -> score -> Excel pipeline (Step 1) | New — verified live twice
risk_scored_vouchers.xlsx | All 7,778 vouchers ranked | Regenerated with vendor_flag_score / vendor_flag_reason columns, synced
Live_Flagged_Vouchers.xlsx | Live-pulled vouchers, ranked and flagged | New, synced
live_daybook_export.xlsx | Raw live Tally pull | Refreshed (76 rows), synced
README.md | Project overview and results summary | Rewritten with corrected figures
SOP_and_Audit_Trail.docx | Project SOP + audit trail | Edited, verified by render
Master_Capstone_Prompt.docx | Full build spec / methodology write-up | Edited, verified by render
Ledger_Sentinel_Explained_Simply.docx | Plain-language project explainer | Edited, verified by render
Tally_MCP_Integration_SOP.docx | Live Tally <-> MCP setup SOP | Edited + new Step 11, verified by render
Ledger_Sentinel_Capstone_Presentation.pptx | 11-slide capstone deck | Slide 6 rebuilt, validated, rendered clean
generate_data.py | Synthetic data generator (Step 1) | Updated — per-vendor ledger structure (15 busy + 1 shell vendor), 9th fraud type (structured disbursement)
tally_daybook_export.xlsx | Input file, no fraud labels | Regenerated (7,778 vouchers)
fraud_answer_key.xlsx | Hidden answer key | Regenerated (278 fraud entries, 9 types)
app_streamlit.py | Interactive dashboard (Step 4) | Updated — fixed a missing stable-sort tiebreak found during this pass, added the Rule 11 vendor screen as its own dashboard section
ai_explainer.py | AI explanation layer (Step 3) | Updated — now unions every Rule 11 vendor flag into the working paper so structuring catches aren't silently dropped for ranking low on risk_score
Auditor_Working_Paper.xlsx | Output of the AI layer | Regenerated (60 entries: top 50 by risk_score + 10 Rule 11 flags)
Rule11_Structuring_Prototype/ | First-draft honest proof (narration-based vendor guess, blended score) | Superseded by the production Rule 11 above; kept as a historical record of the first honest attempt