Final Review Paper - Liquidation

Generated by AuditSignOff Suite UAE - Partner/Manager Review Automation (offline). Software finds and records; the reviewer decides and signs.

| Item | Detail |
| --- | --- |
| Client | SAMPLE HOLDINGS LTD |
| Authority | DIFC |
| Module | B - Liquidation clock and tracker |
| As at | 2026-10-17 |
| Prepared by / Reviewed by | ____________ / ____________ |

1. Summary

| Checks automated | Passed (not listed again) | With exceptions | Assisted - reviewer to confirm | Not run (input missing) | Manual only | High | Medium | Low |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 25 | 4 | 7 | 0 | 14 | 0 | 5 | 2 | 0 |

NOT READY for Partner sign-off: High-severity exceptions are open.

2. Exceptions requiring reviewer action

| Ref | Severity | Finding | Detail | Evidence / location | Expected | Found | Reviewer response | Status / cleared by |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LQ-03.1 | High | FTA notification: overdue | Due 2026-07-03; 106 day(s) overdue as at 2026-10-17 and not recorded as done | 20 business days from appointment letter (weekends only - holiday list empty excluded) | 2026-07-03 | - |  | Open |
| LQ-04.1 | High | VAT TRN deregistration initiated: late | Actioned 2026-08-20, 50 day(s) after the due date 2026-07-01 | 30 days from BR (firm workbook rule) | 2026-07-01 | 2026-08-20 |  | Open |
| LQ-05.1 | High | Earliest report date after creditor block: too early | Report dated/planned 2026-10-05 is 13 day(s) before the earliest permitted date 2026-10-18 | 45 days from last advertisement (2026-09-03) | 2026-10-18 | 2026-10-05 |  | Open |
| LQ-11.1 | High | Legal NOCs / deregistrations outstanding | vat_deregistration, ct_deregistration, authority_portal, labour_visa, establishment_card, esr_aml | NOC tracker | Obtained or NA | Pending |  | Open |
| LQ-14.1 | High | Bank account closed while other clearances are still outstanding | Closure 2026-09-20; outstanding: utilities, vat_deregistration, ct_deregistration, authority_portal, labour_visa, establishment_card, esr_aml | Tracker | Bank closed last | 2026-09-20 |  | Open |
| LQ-10.1 | Medium | Facility NOCs outstanding | utilities | NOC tracker | Obtained or NA | Pending |  | Open |
| LQ-13.1 | Medium | Bank letters outstanding | Bank B (UK): no_liability_letter, closure_letter | Bank tracker | All letters on file | Pending |  | Open |

3. Clock and milestone schedule

| Check | Milestone | Basis | Due / earliest | Actual | Status |
| --- | --- | --- | --- | --- | --- |
| LQ-03 | FTA notification | 20 business days from appointment letter (weekends only - holiday list empty excluded) | 2026-07-03 |  | OVERDUE |
| LQ-04 | VAT TRN deregistration initiated | 30 days from BR (firm workbook rule) | 2026-07-01 | 2026-08-20 | LATE |
| LQ-05 | Earliest report date after creditor block | 45 days from last advertisement (2026-09-03) | 2026-10-18 | 2026-10-05 | TOO EARLY |
| LQ-07 | Liquidation report submitted | Within 12 months of BR | 2027-06-01 |  | PENDING |

4. Exceptions and items not fully checked by the software (checks that passed are not repeated)

EXC = exception (section 2); ASSIST = software extracted the evidence, reviewer confirms; r = not run or manual.

| ID | Area | Check | Class | Status | Note / evidence |
| --- | --- | --- | --- | --- | --- |
| LQ-03 | Clocks | FTA notification within 20 business days of the appointment letter | A | EXC | 1 exception(s) - see section 2 |
| LQ-04 | Clocks | VAT TRN deregistration initiated within 30 days of BR (workbook rule) | A | EXC | 1 exception(s) - see section 2 |
| LQ-05 | Clocks | 45-day creditor block after newspaper advertisement (DIFC, Mainland) before report issue | A | EXC | 1 exception(s) - see section 2 |
| LQ-06 | Clocks | Minimum 14 days between BR and report (DSO/IFZA) unless Partner approved | A | r | Not run: Not a DIFC requirement in firm workbook |
| LQ-08 | Clocks | Expired trade licence: report within 30 days of expiry (DSO/IFZA) | A | r | Not run: Not applicable (authority rule or no expiry date) |
| LQ-09 | Stakeholders | All partners aware of the liquidation; no legal dispute between partners | C | r | Not run: Fill in the tracker: partners.all_informed, partners.dispute |
| LQ-10 | Clearances | Facility NOCs: telecom, utilities, chiller, landlord | A | EXC | 1 exception(s) - see section 2 |
| LQ-11 | Clearances | Legal NOCs: PO Box, VAT, CT, authority portal, labour/visa, establishment card, ESR/AML | A | EXC | 1 exception(s) - see section 2 |
| LQ-12 | Clearances | CT and VAT deregistration status, penalties and late filing | B | r | Not run: Fill in the tracker: vat.returns_filed_up_to_date, vat.penalties_outstanding, ct.returns_filed_up_to_date, ct.penalties_outstanding |
| LQ-13 | Bank | No-liability and closure letters for every bank account, including outside UAE | A | EXC | 1 exception(s) - see section 2 |
| LQ-14 | Bank | Bank account closed only after all other steps are complete | A | EXC | 1 exception(s) - see section 2 |
| LQ-15 | Authority specifics | Authority-specific conditions: DMCC physical submission, DIFC portal balance and PSA refund cleared, advertisement uploaded by liquidator as one file | A | r | Not run: Fill in the tracker: auth.portal_balance_cleared, auth.psa_refund_cleared, auth.advert_one_file |
| LQ-16 | Report | Liquidation report built from TB, GL, SOFP and income statement after adjustments | B | r | Not run: Fill in the tracker: report.built_from_tb, report.adjustments_posted |
| LQ-17 | Report | FTA final communication agrees to the note in the report | B | r | Not run: Fill in the tracker: fta.final_letter_date / fta.final_letter_status |
| LQ-18 | Report | Legal claims and contingent liabilities settled or provided | C | r | Not run: Fill in the tracker: legal.open_claims |
| LQ-21 | Documents | Board Resolution: company, resolution wording, liquidator, date, all shareholders/partners named and signing | A | r | Not run: Upload: Board Resolution |
| LQ-22 | Documents | Statement of Affairs: as-at date, totals recomputed, deficiency flagged, tax creditors, liquidator named | A | r | Not run: Upload: Statement of Affairs |
| LQ-23 | Documents | Liquidator's report: required sections, dates and advertisement dates agree to the tracker, figures agree to the Statement of Affairs | A | r | Not run: Upload: Liquidator's report |
| LQ-24 | Documents | Trial balance (optional) balances and agrees to the Statement of Affairs and report | A | r | Not run: Upload the trial balance (optional) to run this check |
| LQ-25 | Documents | Corporate Tax and VAT registration evidenced; deregistration initiated; final CT return addressed in the report | A | r | Not run: Upload the CT/VAT registration certificate or FTA letter (or the report/SOA) to check registration status |
| LQ-26 | Documents | Company name and liquidator name consistent across all documents | A | r | Not run: Upload at least two of: Board Resolution, Statement of Affairs, Liquidator's report, licence |

5. Sign-off

|  | Prepared by | First review | Manager review | Partner review |
| --- | --- | --- | --- | --- |
| Name |  |  |  |  |
| Date |  |  |  |  |
| Sign |  |  |  |  |

Input integrity (SHA-256): liq_difc_breach.yaml: c4f935a12fc71921...