## Summary
Metric | Value
Period | 2026-10-01 to 2026-10-17
Total hours logged | 13.92
Additional / ad-hoc hours | 4.33
Additional work % of time | 31.1
Tasks completed | 7
Tasks still open | 3
Open tasks carried forward | 3

## Hours by category
category | Hours
Additional / ad-hoc | 4.33
Client work | 8
Internal | 0.67
Learning | 0.92

## KPIs
KPI | Period | Month | Type | Category | Target | Actual | Achievement %
Tasks completed this year | Yearly |  | Tasks completed | All | 120 | 7 | 5.8
Tasks completed this month | Monthly | 10 | Tasks completed | All | 10 | 7 | 70
Billable hours this month | Monthly | 10 | Hours logged | Client work | 20 | 8 | 40
Client calls this month | Monthly | 10 | Manual count | All | 8 | 3 | 37.5

## Tasks
id | title | category | client | planned_min | status | original_date | scheduled_date | carried_count | completed_on | notes | actual_min | age_days | flag
1 | GST return working - Client A | Client work | Client A | 90 | Done | 2026-10-03 | 2026-10-03 | 0 | 2026-10-05 |  | 80 | 2
2 | TDS reconciliation - Client B | Client work | Client B | 120 | Done | 2026-10-04 | 2026-10-04 | 0 | 2026-10-08 |  | 135 | 4
3 | Bank reconciliation - Client C | Client work | Client C | 60 | Done | 2026-10-05 | 2026-10-05 | 0 | 2026-10-09 |  | 75 | 4
5 | Update office compliance tracker | Internal |  | 45 | Done | 2026-10-07 | 2026-10-07 | 0 | 2026-10-10 |  | 40 | 3
6 | Urgent notice reply - Client A | Additional / ad-hoc | Client A | 0 | Done | 2026-10-08 | 2026-10-08 | 0 | 2026-10-13 |  | 150 | 5
7 | Partner asked for MIS pack | Additional / ad-hoc |  | 0 | Done | 2026-10-09 | 2026-10-09 | 0 | 2026-10-14 |  | 110 | 5
8 | Learn Streamlit basics | Learning |  | 60 | Done | 2026-10-10 | 2026-10-10 | 0 | 2026-10-15 |  | 55 | 5
4 | Audit working paper - Client D | Client work | Client D | 180 | In progress | 2026-10-06 | 2026-10-17 | 1 |  |  | 190 | 11 | Carried forward
9 | Prepare engagement letters | Admin |  | 60 | Not started | 2026-10-11 | 2026-10-17 | 1 |  |  | 0 | 6 | Carried forward
10 | Month-end review - Client B | Client work | Client B | 90 | Not started | 2026-10-12 | 2026-10-17 | 1 |  |  | 0 | 5 | Carried forward

## Time entries
id | entry_date | minutes | note | task_id | title | category | client | is_additional
1 | 2026-10-05 | 80 |  | 1 | GST return working - Client A | Client work | Client A | 0
2 | 2026-10-07 | 70 |  | 2 | TDS reconciliation - Client B | Client work | Client B | 0
3 | 2026-10-08 | 65 |  | 2 | TDS reconciliation - Client B | Client work | Client B | 0
4 | 2026-10-09 | 75 |  | 3 | Bank reconciliation - Client C | Client work | Client C | 0
7 | 2026-10-10 | 40 |  | 5 | Update office compliance tracker | Internal |  | 0
5 | 2026-10-11 | 100 |  | 4 | Audit working paper - Client D | Client work | Client D | 0
6 | 2026-10-12 | 90 |  | 4 | Audit working paper - Client D | Client work | Client D | 0
8 | 2026-10-13 | 150 |  | 6 | Urgent notice reply - Client A | Additional / ad-hoc | Client A | 1
9 | 2026-10-14 | 110 |  | 7 | Partner asked for MIS pack | Additional / ad-hoc |  | 1
10 | 2026-10-15 | 55 |  | 8 | Learn Streamlit basics | Learning |  | 0

## About
Developed by CA Sapan